## Waterfall RACI
Waterfall Project RACI Template
Copy this tab per project. Replace phase names/rows and roles as needed - never more than one A per row.
Activity / Deliverable | Sponsor | Program/ Project Mgr | Business Analyst | Solution Architect | Dev Lead | QA Lead | Security/ Compliance | Change Mgmt | End Users/ Stakeholders
Initiation
Business case & charter | A | R | C | I |  |  | C |  | C
Stakeholder identification | I | A/R | C |  |  |  |  | C | C
Budget & resource approval | A | R | C | C | I | I
Requirements
Requirements gathering |  | C | A/R | C | C | C | C | I | R
Requirements sign-off | A | R | R | C | I | I | C | I | C
Scope baseline | A | R | C | C | C | I |  | I | I
Design
Solution/technical design |  | C | C | A/R | C | C | C
Design review & approval | A | R | C | R | C | C | C
Security/architecture review | C R: C; C C: C; C I: C; C I: C; C C: A/R
Development
Build/development | C R: I; C C: C; C I: A/R; C I: I
Code review | C C: C; C I: A/R; C I: C; C C: C
Unit testing | C I: A/R; C I: C
Testing
Test plan development |  | C | C | C | C | A/R | C
System integration testing |  | I | C | C | C | A/R | C
UAT execution & sign-off | A | R | C |  | I | C |  | I | R
Defect resolution | C R: I; C C: C; C I: A/R; C I: R
Deployment
Deployment/release plan | A | R | I | C | C | C | C | R | I
Go-live execution | A | R | I | C | R | C | C | C | I
Post-launch support/hypercare | I | C |  | C | A/R | R |  | C | I
Closure
Lessons learned | I | A | R | R | R | R | C | C
Project closure & sign-off | A | R | C | I | I | I |  |  | I
Legend
R | I: Responsible - does the work to complete the task
A | I: Accountable - owns the outcome and signs off; never more than one per row, exactly one on any row with a real decision or sign-off
C | I: Consulted - two-way input sought before/during the work
I | I: Informed - kept updated on progress or outcome, one-way
- Rules of thumb: never more than one A per row. R can be shared, A cannot.
- If a role has no R/A/C/I on a row, leave the cell blank - do not mark every role on every row.
- Validate row-by-row: no row with more than one A, and no row with a real decision or sign-off that has none.

## Agile RACI
Agile Project/Program RACI Template
Copy this tab per team/program. Substitute Scrum roles for Kanban/SAFe as needed - never more than one A per row.
Activity / Deliverable | Product Owner | Scrum Master | Dev Team | QA/Test | Solution Architect | Release Mgr | Security/ Compliance | Stakeholders/ Sponsor
Program/Release Setup
Vision & roadmap | R, A | C | I |  | C | I |  | C
Release/PI planning | A | R | C | C | C | C | C | C
Backlog prioritization | A | C | I |  | I |  |  | C
Sprint Cadence
Backlog refinement | A | C | R | C | C
Sprint planning | A | R | R | C | C | I
Daily standup |  | R | R | I
Story/epic definition & acceptance criteria | A | C | R | C | C
Development |  |  | R | I | C
Code review |  |  | R | C | C |  | C
Quality & Review
Sprint testing/QA | C |  | C | R, A |  |  | C
Security scan/review | I |  | C | C | C |  | R, A
Sprint review/demo | A | R | R | C | I | I |  | C
Sprint retrospective | R | A | R | R
Release
Release readiness review | A | R | C | C | C | R | C | I
Deployment/release | I | C | C | C | C | A | C | I
Post-release monitoring | I | C | R | R | C | A |  | I
Legend
R | A: Responsible - does the work to complete the task
A | A: Accountable - owns the outcome and signs off; never more than one per row, exactly one on any row with a real decision or sign-off
C | A: Consulted - two-way input sought before/during the work
I | A: Informed - kept updated on progress or outcome, one-way
- Rules of thumb: never more than one A per row. R can be shared, A cannot.
- If a role has no R/A/C/I on a row, leave the cell blank - do not mark every role on every row.
- Validate row-by-row: no row with more than one A, and no row with a real decision or sign-off that has none.